## Cover
RISK REGISTER
ISO/IEC 27001:2022 — Information Security Risk Assessment
NorthStar Retail Ltd
Version: v1.4
Date: 2 April 2026
Classification: Internal — Restricted
Owner: team member-2 (Risk Lead / Group Assessment)
Methodology: 5x5 qualitative likelihood-impact matrix aligned to ISO/IEC 27001:2022 risk assessment
Risk scoring: 1–5 Low · 6–10 Medium · 11–15 High · 16–25 Critical
Treatment options: Mitigate / Transfer / Accept / Avoid
Review cycle: Critical risks monthly during rollout; all risks quarterly or on significant change

## Risk Heatmap
NorthStar Retail Ltd - Inherent Risk Heatmap (Impact rows x Likelihood columns)
| 1 | 2 | 3 | 4 | 5 | LEGEND
IMPACT | LIKELIHOOD |  |  |  |  | CRITICAL (16–25)
5 | 5 | 10 | R-04, R-05, R-07, R-09 | R-02 | 25 | HIGH (11–15)
4 | 4 | 8 | R-03, R-06, R-10, R-11 | R-12 | R-01 | MEDIUM (6–10)
3 | 3 | 6 | 9 | R-08 | 15 | LOW (1–5)
2 | 2 | 4 | 6 | 8 | 10
1 | 1 | 2 | 3 | 4 | 5
Heatmap basis | Inherent risk scores before additional treatment
Risk Summary | Inherent Score | Residual Score | Treatment
Risk ID | Inherent Score | Target Residual Score | Treatment
R-01 | Critical (20) | High (12) | Mitigate
R-02 | Critical (20) | High (12) | Mitigate
R-03 | High (12) | Medium (8) | Mitigate / Transfer
R-04 | High (15) | Medium (10) | Mitigate
R-05 | High (15) | Medium (10) | Mitigate / Transfer
R-06 | High (12) | Medium (8) | Mitigate
R-07 | High (15) | High (12) | Mitigate / Transfer
R-08 | High (12) | Medium (8) | Mitigate
R-09 | High (15) | Medium (10) | Mitigate
R-10 | High (12) | Medium (8) | Mitigate
R-11 | High (12) | Medium (6) | Mitigate
R-12 | Critical (16) | Medium (10) | Mitigate

## Risks
Risk ID | Date Risk Raised | Raised by | Affected Asset / Process | Risk Owner | Threat | Vulnerability | Risk Statement | Risk Likelihood | Risk Consequence | Risk Rating | Current Risk Comments | Control areas for existing controls | Risk Treatment Decision | Risk Treatment Plan | Control areas for new treatment measures | Treated Residual Risk Likelihood | Treated Residual Risk Consequence | Treated Residual Risk | Date of Risk Owner's Acceptance / Treatment Approval | Risk Treatment Owner | Date Risk Treatment due | Date Risk Treatment Implemented | Date of Review and Nature of Updates
R-01 | 31/03/2026 | Lucas (Risk Lead) | Microsoft 365, email, finance approvals | Head of IT | Phishing and credential theft | Partial MFA, weak joiner-mover-leaver process, limited user reporting | Microsoft 365 and finance accounts may be compromised through phishing, leading to fraud, mailbox compromise and reportable data exposure. | 5 (Almost Certain) | 4 (Major) | Critical (20) | Some MFA exists but coverage is incomplete and phishing reporting is informal, so finance and mailbox compromise remain credible. | 5.15 Access control 5.17 Authentication information 6.3 Information security awareness, education and training | Mitigate | Enforce MFA for all users, add conditional access, strengthen email authentication, improve phishing reporting, and separate admin accounts. | 5.16 Identity management 5.17 Authentication information 5.18 Access rights 6.8 Information security event reporting 8.5 Secure authentication 8.23 Web filtering | 3 (Possible) | 4 (Major) | High (12) | 31/03/2026 | Head of IT | 30/04/2026 |  | 31/03/2026 - Initial assessment recorded. Next review due 30/04/2026.
R-02 | 31/03/2026 | Lucas (Risk Lead) | Endpoints, servers, warehouse and office systems | Head of IT | Ransomware and business interruption | Patch gaps, flat network, limited EDR, weak restore testing | Malware or ransomware may disrupt endpoints and core operational systems, leading to sales outage, fulfilment disruption and costly recovery. | 4 (Likely) | 5 (Severe) | Critical (20) | Basic anti-malware and cloud backups exist, but recovery assurance is weak because backups are not routinely restore-tested. | 8.7 Protection against malware 8.8 Management of technical vulnerabilities 8.13 Information backup | Mitigate | Deploy EDR, prioritise patching, segment networks, harden admin access, and test isolated backups and restore procedures. | 8.7 Protection against malware 8.8 Management of technical vulnerabilities 8.13 Information backup 8.22 Segregation of networks 8.2 Privileged access rights 5.29 Information security during disruption 5.30 ICT readiness for business continuity | 3 (Possible) | 4 (Major) | High (12) | 31/03/2026 | Head of IT | 30/04/2026 |  | 31/03/2026 - Initial assessment recorded. Next review due 30/04/2026.
R-03 | 31/03/2026 | Lucas (Risk Lead) | E-commerce website and mobile app | Head of IT | DoS or DDoS outage | Single points of failure, limited capacity testing, untested response | DoS or DDoS activity may make the website or mobile app unavailable, causing direct online revenue loss and customer abandonment. | 3 (Possible) | 4 (Major) | High (12) | Current hosting provides basic resilience, but NorthStar has limited tested response capability for a sustained outage. | 8.6 Capacity management 8.21 Security of network services 8.14 Redundancy of information processing facilities | Mitigate / Transfer | Introduce upstream DDoS protection, strengthen CDN and WAF coverage, tune rate limiting, and rehearse outage response with service providers. | 8.6 Capacity management 8.20 Network security 8.21 Security of network services 8.14 Redundancy of information processing facilities 5.30 ICT readiness for business continuity | 2 (Unlikely) | 4 (Major) | Medium (8) | 31/03/2026 | Head of IT | 30/06/2026 |  | 31/03/2026 - Initial assessment recorded. Next review due 30/06/2026.
R-04 | 31/03/2026 | Lucas (Risk Lead) | Cloud CRM, customer database, SaaS admin portals | Head of IT | Cloud or SaaS data exposure | Weak configuration governance, excessive sharing, limited alerts | Customer data may be exposed through insecure cloud or SaaS configuration, leading to regulatory scrutiny, remediation cost and trust loss. | 3 (Possible) | 5 (Severe) | High (15) | Some role-based access exists, but configuration changes and risky sharing activity are not consistently governed or monitored. | 5.23 Information security for use of cloud services 5.15 Access control | Mitigate | Apply secure cloud configuration standards, least privilege, admin separation, change alerts, and periodic access reviews. | 5.23 Information security for use of cloud services 5.15 Access control 5.16 Identity management 5.18 Access rights 8.9 Configuration management 8.16 Monitoring activities 5.34 Privacy and protection of PII | 2 (Unlikely) | 5 (Severe) | Medium (10) | 31/03/2026 | Head of IT | 30/06/2026 |  | 31/03/2026 - Initial assessment recorded. Next review due 30/06/2026.
R-05 | 31/03/2026 | Lucas (Risk Lead) | POS, payment gateway, online checkout | Finance Manager | Payment environment compromise | Weak segmentation, inconsistent patching, third-party script risk | Payment systems may be compromised through weak segmentation, patching gaps or checkout script risk, causing fraud exposure and disruption to card payment processing. | 3 (Possible) | 5 (Severe) | High (15) | Payment processing is partly outsourced, but NorthStar still relies on its own POS, checkout integration and supporting environment. | 8.24 Use of cryptography 8.20 Network security 8.26 Application security requirements | Mitigate / Transfer | Reduce PCI scope, segment payment systems, harden POS, monitor checkout scripts, and maintain a payment-specific incident response plan. | 8.22 Segregation of networks 8.9 Configuration management 8.15 Logging 8.16 Monitoring activities 5.24 Information security incident management planning and preparation 8.26 Application security requirements | 2 (Unlikely) | 5 (Severe) | Medium (10) | 31/03/2026 | Finance Manager | 30/06/2026 |  | 31/03/2026 - Initial assessment recorded. Next review due 30/06/2026.
R-06 | 31/03/2026 | Lucas (Risk Lead) | Refunds, HR data, admin tools | HR Manager | Insider misuse or privilege abuse | Excess access, weak segregation of duties, limited monitoring | Excessive access or weak segregation of duties may enable insider misuse, causing refund fraud, data leakage or operational harm. | 3 (Possible) | 4 (Major) | High (12) | Baseline controls exist, but refund and admin activities still depend too heavily on broad access and limited monitoring. | 5.3 Segregation of duties 5.15 Access control 6.1 Screening | Mitigate | Tighten RBAC, apply refund thresholds, review access regularly, and monitor high-risk actions with defined escalation. | 5.3 Segregation of duties 5.18 Access rights 8.2 Privileged access rights 8.15 Logging 8.16 Monitoring activities 6.4 Disciplinary process | 2 (Unlikely) | 4 (Major) | Medium (8) | 31/03/2026 | HR Manager | 30/06/2026 |  | 31/03/2026 - Initial assessment recorded. Next review due 30/06/2026.
R-07 | 31/03/2026 | Lucas (Risk Lead) | Payment, logistics, payroll, SaaS suppliers | Compliance Lead | Third-party compromise or outage | Limited assurance, unclear contractual duties, dependency concentration | A critical supplier may suffer compromise or outage, leading to service disruption, indirect breach exposure and regulatory impact on NorthStar. | 3 (Possible) | 5 (Severe) | High (15) | Key processors have DPAs, but supplier assurance and contingency planning are not yet mature or consistently documented. | 5.19 Information security in supplier relationships 5.20 Addressing information security within supplier agreements | Mitigate / Transfer | Tier suppliers, strengthen security clauses, require incident notification, review assurance regularly, and define contingency options for critical suppliers. | 5.19 Information security in supplier relationships 5.20 Addressing information security within supplier agreements 5.21 Managing information security in the ICT supply chain 5.22 Monitoring, review and change management of supplier services 5.23 Information security for use of cloud services 5.31 Legal, statutory, regulatory and contractual requirements | 3 (Possible) | 4 (Major) | High (12) | 31/03/2026 | Compliance Lead | 30/06/2026 |  | 31/03/2026 - Initial assessment recorded. Next review due 30/06/2026.
R-08 | 31/03/2026 | Lucas (Risk Lead) | Laptops, mobiles, store and warehouse devices | Head of IT | Device loss or theft | Inconsistent encryption, limited MDM, cached credentials | Lost or stolen user devices may expose business or personal data and provide an initial access path into corporate services. | 4 (Likely) | 3 (Moderate) | High (12) | Device controls are inconsistent across stores, warehouse and mobiles, increasing exposure if assets are lost or stolen. | 8.1 User endpoint devices 8.24 Use of cryptography 7.9 Security of assets off-premises | Mitigate | Apply full-disk encryption, mobile device management, remote wipe, conditional access, and accurate asset inventory. | 8.1 User endpoint devices 8.24 Use of cryptography 7.9 Security of assets off-premises 8.5 Secure authentication 5.9 Inventory of information and other associated assets | 4 (Likely) | 2 (Minor) | Medium (8) | 31/03/2026 | Head of IT | 30/06/2026 |  | 31/03/2026 - Initial assessment recorded. Next review due 30/06/2026.
R-09 | 31/03/2026 | Lucas (Risk Lead) | Backup and recovery services | Head of IT | Backup failure during major incident | Backups not isolated, shared admin access, untested recovery | Backup failure during a major incident may prevent timely recovery, extending outage duration and worsening business impact. | 3 (Possible) | 5 (Severe) | High (15) | Backups exist, but they are not yet isolated or routinely tested against realistic recovery scenarios. | 8.13 Information backup | Mitigate | Separate backup credentials, use immutable copies, define recovery targets, and routinely test restore procedures. | 8.13 Information backup 5.29 Information security during disruption 5.30 ICT readiness for business continuity 8.2 Privileged access rights | 2 (Unlikely) | 5 (Severe) | Medium (10) | 31/03/2026 | Head of IT | 30/06/2026 |  | 31/03/2026 - Initial assessment recorded. Next review due 30/06/2026.
R-10 | 31/03/2026 | Lucas (Risk Lead) | Inventory, ERP, pricing, warehouse picking | Warehouse Manager | Integrity failure in stock or pricing data | Weak change control, broad access, limited validation | Unauthorised or erroneous changes to inventory or pricing data may cause stock errors, fulfilment failures and margin loss. | 3 (Possible) | 4 (Major) | High (12) | Basic access control exists, but change control and integrity checks are too limited for revenue-critical data. | 5.15 Access control | Mitigate | Introduce change approvals, restrict privileged access, add integrity checks, and alert on unusual bulk changes. | 8.32 Change management 8.2 Privileged access rights 8.15 Logging 8.16 Monitoring activities 8.31 Separation of development, test and production environments | 2 (Unlikely) | 4 (Major) | Medium (8) | 31/03/2026 | Warehouse Manager | 30/06/2026 |  | 31/03/2026 - Initial assessment recorded. Next review due 30/06/2026.
R-11 | 31/03/2026 | Lucas (Risk Lead) | Cookies, marketing preferences, email and SMS campaigns | Marketing Manager | Consent or preference non-compliance | Weak consent evidence, unclear cookie categories, poor suppression control | Weak consent and preference management may lead to non-compliant cookie or direct marketing activity, creating regulatory and reputational risk. | 3 (Possible) | 4 (Major) | High (12) | NorthStar has baseline consent mechanisms, but evidence quality and governance over cookies and marketing rules are weak. | 5.31 Legal, statutory, regulatory and contractual requirements 5.34 Privacy and protection of PII | Mitigate | Implement a consent platform, categorise cookies clearly, add campaign sign-off, and retain auditable consent evidence. | 5.31 Legal, statutory, regulatory and contractual requirements 5.34 Privacy and protection of PII 5.33 Protection of records 5.36 Compliance with policies, rules and standards for information security | 2 (Unlikely) | 3 (Moderate) | Medium (6) | 31/03/2026 | Marketing Manager | 30/06/2026 |  | 31/03/2026 - Initial assessment recorded. Next review due 30/06/2026.
R-12 | 31/03/2026 | Lucas (Risk Lead) | Logging and monitoring across key systems | Head of IT | Delayed detection and response | Fragmented logs, limited alerting, unclear escalation | Fragmented logging and weak escalation may delay breach detection and response, increasing impact, cost and reportability. | 4 (Likely) | 4 (Major) | Critical (16) | Some systems retain logs, but visibility is fragmented and escalation depends too heavily on ad hoc action. | 8.15 Logging | Mitigate | Centralise logging, define detection rules, rehearse playbooks, and formalise reporting and escalation routes. | 8.15 Logging 8.16 Monitoring activities 5.24 Information security incident management planning and preparation 5.25 Assessment and decision on information security events 5.26 Response to information security incidents 5.27 Learning from information security incidents 5.28 Collection of evidence | 2 (Unlikely) | 5 (Severe) | Medium (10) | 31/03/2026 | Head of IT | 30/04/2026 |  | 31/03/2026 - Initial assessment recorded. Next review due 30/04/2026.

## Field Descriptors
Field Name | Definition / Instructions
Risk ID | Running risk identifier for the NorthStar register.
Date Risk Raised | Date the risk was formally recorded in the assessment.
Raised by | Person who identified or documented the risk.
Affected Asset / Process | Business asset, service, system or process affected by the risk.
Risk Owner | Primary accountable owner for managing the risk.
Threat | The event or actor that could cause harm.
Vulnerability | The weakness that makes the threat credible.
Risk Statement | Concise statement linking asset, threat and business consequence.
Risk Likelihood | Current likelihood before new treatment. NorthStar scale: 5 Almost Certain to 1 Rare.
Risk Consequence | Current business impact before new treatment. NorthStar scale: 5 Severe to 1 Insignificant.
Risk Rating | Current inherent risk band derived from likelihood x consequence.
Current Risk Comments | Comments on existing controls and why the risk still matters.
Control areas for existing controls | Relevant ISO/IEC 27001:2022 Annex A control references already in place.
Risk Treatment Decision | Planned response: usually Mitigate, and Transfer where contractual or specialist risk-sharing is used.
Risk Treatment Plan | Summary of additional treatment measures to reduce the risk.
Control areas for new treatment measures | Relevant ISO/IEC 27001:2022 Annex A control references for the planned treatment.
Treated Residual Risk Likelihood | Expected likelihood after treatment is implemented.
Treated Residual Risk Consequence | Expected impact after treatment is implemented.
Treated Residual Risk | Expected residual risk band after treatment.
Date of Risk Owner's Acceptance / Treatment Approval | Date the risk owner approved the treatment plan or accepted the risk position.
Risk Treatment Owner | Person accountable for implementing the treatment plan.
Date Risk Treatment due | Target date for the main treatment actions.
Date Risk Treatment Implemented | Actual implementation date when treatment is completed; blank if not yet completed.
Date of Review and Nature of Updates | Review trail noting when the risk was reviewed and any changes or next review date.

## Summary
Risk Register — Summary
Metric | Value
Total risks identified | 12
Critical risks (score 16–25) | 3 (R-01, R-02, R-12)
High risks (score 11–15) | 9 (R-03 to R-11)
Medium risks (score 6–10) | 0 inherent; residual risks reduce to medium or high
Treatment: Mitigate | 9 risks
Treatment: Mitigate / Transfer | 3 risks (R-03, R-05, R-07)
Risk methodology | 5x5 qualitative likelihood-impact matrix aligned to ISO/IEC 27001:2022 risk assessment
Framework | ISO/IEC 27001:2022 + ISO/IEC 27002:2022
Risk register owner | Lucas (Risk Lead) — reviewed by IT Manager & DPO
Review frequency | Critical risks monthly during rollout; all risks quarterly or on significant change
Version | v1.4
Date | 2 April 2026
Next review | 30 April 2026 (critical risks); 30 June 2026 (full register)

## Risk Criteria
NorthStar Retail Ltd - Risk Criteria
Likelihood scale |  |  | 5x5 qualitative matrix
Score | Label | Definition |  | Impact ->
5 | Almost Certain | Expected to occur frequently or in current operating conditions. | Likelihood v | 1 | 2 | 3 | 4 | 5
4 | Likely | Could occur in normal operations and has credible recent triggers. | 5 | Low (5) | Medium (10) | High (15) | Critical (20) | Critical (25)
3 | Possible | Could occur but not routinely; realistic under current controls. | 4 | Low (4) | Medium (8) | High (12) | Critical (16) | Critical (20)
2 | Unlikely | Could occur, but only under less common circumstances. | 3 | Low (3) | Medium (6) | Medium (9) | High (12) | High (15)
1 | Rare | Uncommon and not expected in normal operating conditions. | 2 | Low (2) | Low (4) | Medium (6) | Medium (8) | Medium (10)
|  |  | 1 | Low (1) | Low (2) | Low (3) | Low (4) | Low (5)
Impact scale
Score | Label | Definition
5 | Severe | Major operational failure, serious regulatory exposure, or sustained trust and revenue damage.
4 | Major | Material disruption, reportable incident risk, or significant financial and reputational impact.
3 | Moderate | Noticeable service, financial or compliance impact requiring management action.
2 | Minor | Contained impact with limited operational or customer effect.
1 | Insignificant | Minimal effect, easily contained within normal operations.
Risk bands
Score range | Band | Required response
16-25 | Critical | Immediate treatment and senior management oversight.
11-15 | High | Formal treatment plan with tracked ownership.
6-10 | Medium | Manage, monitor and review against appetite.
1-5 | Low | Accept or monitor within appetite.

## Abbreviations
Abbreviation | Meaning | Notes
CRM | Customer Relationship Management | Customer and support data environment
ERP | Enterprise Resource Planning | Core stock, pricing, and operational planning system
POS | Point of Sale | In-store payment and checkout systems
SaaS | Software as a Service | Cloud-delivered applications used by NorthStar
PII | Personally Identifiable Information | Used in privacy and data protection control references
MFA | Multi-Factor Authentication | Key treatment for phishing and credential compromise
EDR | Endpoint Detection and Response | Helps detect and contain malware and ransomware activity
DPO | Data Protection Officer | Responsible for privacy governance and oversight
RTO | Recovery Time Objective | Target recovery time after an incident
RPO | Recovery Point Objective | Target amount of acceptable data loss
WAF | Web Application Firewall | Helps protect web applications and online services
CDN | Content Delivery Network | Supports website resilience and DDoS response
ISMS | Information Security Management System | The formal management system proposed for NorthStar
SoA | Statement of Applicability | Documents which Annex A controls apply and why
Annex A | ISO/IEC 27001:2022 control set | Control references in the register and SoA point to Annex A
Risk ID | NorthStar risk numbering | R-01 to R-12 identify individual risk entries
Treatment | Planned response to risk | Used here as Mitigate, Transfer, Accept, or Avoid
Notes | Control references in the risk register use ISO/IEC 27001:2022 Annex A naming. Business and technical abbreviations are expanded here for readability.